TRACK 3: AMAZON KDP SELF-PUBLISHING

Master Step-by-Step Checklist

For Steve Haggerty — All 7 Books

Built: June 21, 2026

Part of the 3-Pronged Publishing Strategy

Prong 1: Literary Agent  |  Prong 2: Traditional Publisher  |  Prong 3: Amazon KDP ← YOU ARE HERE

# Table of Contents

Phase 0: Prerequisites — Get the foundation right before launch

Phase 1: Foundation (Days 1-14) — Categories, keywords, A+ Content, Author Central

Phase 2: Build the Machine (Days 7-21) — Email list, reviews, pricing strategy

Phase 3: Launch Sequence — 6-week ACAT re-launch timeline

Phase 4: Amazon Ads — Campaign setup and optimization

Phase 5: Promotional Tools — Free promos, countdown deals, newsletter swaps

Phase 6: Church Network Activation — Your unfair advantage

Year 1 Target — Revenue goals and metrics

Reference Documents — Links to all detailed guides

# How to Use This Document

Each task has a checkbox ☐. Mark it off as you complete it. The companion documents (linked at the end) have the full detailed instructions for each phase. This is your master roadmap — the others are your reference manuals.

Order matters. Complete Phase 0 before Phase 1. Phase 1 before Phase 2. Some phases overlap (e.g., email list starts in Phase 2 but you should begin collecting emails immediately). Follow the sequence and don't skip ahead.

# Phase 0: Prerequisites

Before anything else — get these basics in place. Estimated time: 2-3 hours.

☐ Sign up for Amazon KDP (kdp.amazon.com) — use your existing Amazon account

☐ Claim your Author Central page (author.amazon.com) — link ALL 7 books to one profile

☐ Install MailerLite (free account) — start building your email list

☐ Set up Amazon Ads account — linked to KDP

☐ Confirm all 7 books have correct pricing (already done per strategy doc)

☐ Read the full strategy plan: amazon_kdp_strategy.docx

☐ Review companion docs: ACAT Launch Day Plan, Ads Guide, Drafts (listed at end)

# Phase 1: Foundation (Days 1-14)

Category selection, keyword optimization, A+ Content, Author Central setup.

## 1.1 Category Selection

This is the highest-impact lever. Amazon categories determine which bestseller lists you appear on.

☐ ACAT → Request 4 categories: Christian Science Fiction & Fantasy, Christian Thriller & Suspense, Time Travel Science Fiction, Religious Science Fiction & Fantasy

☐ Five Letters → Christian Contemporary Fiction, Friendship Fiction, Small Town & Rural Fiction, Christian Romance

☐ Darkly → Christian Suspense, Psychological Thrillers, Crime Thrillers

☐ A Flash of Steel → Military Science Fiction, Adventure Science Fiction, War & Military Action Fiction

☐ Lucy in the Sky → (ask Steve for genre confirmation)

☐ Email Amazon Seller Support to add 2 bonus categories per book (KDP only gives 2, you can request 2 more)

## 1.2 Keyword Backend Optimization

Amazon gives 7 keyword fields (50 bytes each ≈ 7 words). That's 49 keyword slots total.

☐ Research keywords per book using Amazon autocomplete + competitor ASINs

☐ Fill all 7 backend keyword fields for ACAT (highest priority)

☐ Fill backend keywords for Five Letters, Darkly, Flash of Steel

☐ Fill keywords for short story collections (Test of Faith, One-Eyed Ted)

☐ Fill keywords for Lucy in the Sky

## 1.3 A+ Content (Enhanced Brand Content)

☐ Create A+ Content for ACAT — 4 modules: hero image with tagline, author story, comparison chart, mission statement (50% to church)

☐ Publish A+ Content for Five Letters

☐ Publish A+ Content for Darkly

☐ Publish A+ Content for A Flash of Steel

☐ Publish A+ Content for short story collections

☐ Reference: acat_launch_day_plan.docx has exact module text

## 1.4 Author Central Setup

☐ Go to author.amazon.com and claim/update your profile

☐ Update author bio — remove stale references to "2020" and "book 2 by end of 2023"

☐ Add author photo (professional headshot)

☐ Link all 7 books to your author page

☐ Enable Amazon Author Follow button

☐ Reference: ACAT_Author_Bio.docx has the updated bio text

# Phase 2: Build the Machine (Days 7-21)

Email list, reviews, pricing strategy.

## 2.1 Email List — THE #1 ASSET

80% of millionaire authors have an email list. Start now — it compounds.

☐ Set up MailerLite signup form (free, up to 1,000 subscribers)

☐ Create a lead magnet: "ACAT First 3 Chapters" PDF + your author story

☐ Add signup link to your Author Central page

☐ Add signup link to your Amazon book descriptions (use "Also visit" link)

☐ Add signup link to any website or social media you maintain

☐ Prepare first welcome email sequence (3 emails: welcome, your story, what's next)

## 2.2 Review Strategy

Reviews are the gate. 20+ reviews = ads work. 50+ = algorithm starts boosting you.

☐ Enroll in KDP Select / Kindle Unlimited (ACAT — already done ✅)

☐ Email 20 Christian fiction bloggers for review consideration (template in catch22_drafts.docx)

☐ Ask friends and family for honest Amazon reviews

☐ Use Santa's church network — small group ACAT reading → reviews

☐ Target: 20 reviews in 60 days

☐ Target: 50 reviews by end of Year 1

## 2.3 Pricing Strategy

Current prices are set. ACAT is in KU. Strategy: use $0.99 promos to build momentum, then raise.

☐ Confirm current pricing on ALL 7 books (already set per Jun 9 session)

☐ Plan first $0.99 promo for ACAT (use KDP Select Free Book Promo)

☐ Set up price anchor: KU for discovery, $7.99 Kindle for revenue

# Phase 3: Launch Sequence — The ACAT Re-Launch

This is a 6-week timeline. The detailed hour-by-hour plan is in acat_launch_day_plan.docx.

## Week 1: Pre-Launch

☐ Finalize all pricing and categories

☐ Publish A+ Content

☐ Update Author Central bio

☐ Set up MailerLite with lead magnet

☐ Prepare launch email sequence

☐ Line up 5-10 early reviewers (friends, church, family)

## Week 2: Soft Launch

☐ Launch first Amazon ad campaign ($5/day auto-target)

☐ Send launch email to your list

☐ Activate church small group reading program (Santa's job)

☐ Request bonus categories from Amazon Seller Support

☐ Monitor early sales and reviews

## Week 3: Momentum

☐ Review ad performance — kill zeros, pause losers, double winners

☐ Run first KDP Select Free Book Promo (5 days free)

☐ Send follow-up email to list

☐ Submit to BookBub for Featured Deal consideration

## Week 4: Optimization

☐ Analyze free promo results (downloads → reviews)

☐ Adjust ad bids based on data

☐ Start newsletter swap outreach (find 3 Christian fiction authors)

☐ Prepare Kindle Countdown Deal ($0.99 → $3.99)

## Week 5-6: Scale

☐ Launch second ad campaign (manual-target, competitor ASINs)

☐ Increase daily ad spend to $15/day if ACoS is healthy

☐ Run Kindle Countdown Deal

☐ Begin cross-promotion with other Christian fiction authors

☐ Compile learnings and repeat for Five Letters

# Phase 4: Amazon Ads (Ongoing)

Full campaign details in catch22_ads_guide.docx. Start small, scale winners.

## 4.1 Campaign Structure

☐ Campaign 1: Auto-target ($5/day) — let Amazon find the audience

☐ Campaign 2: Manual-target, broad ($5/day) — 30 keywords from ads guide

☐ Campaign 3: Manual-target, competitor ASINs ($5/day) — 22 ASINs from ads guide

☐ Total daily spend: $15/day max ($450/month)

## 4.2 Optimization Rules

☐ Don't touch campaigns for the first 7 days — let them learn

☐ Day 8: Kill keywords/ASINs with zero impressions

☐ Day 8: Pause keywords with high spend (>$3) and zero sales

☐ Day 8: Double bids on keywords with ACoS under 30%

☐ Weekly review: 15 minutes every Sunday

# Phase 5: Promotional Tools

## 5.1 KDP Select Free Book Promo

☐ Schedule ACAT for 5 free days during launch window

☐ Promote free days via email list, social media, church network

☐ Goal: 500+ free downloads → converts to reviews and paid sales

## 5.2 Kindle Countdown Deal

☐ Schedule ACAT Countdown Deal ($0.99 → $3.99 → $7.99)

☐ Use countdown banner in Amazon search results

☐ Promote via email and social media during deal window

## 5.3 Goodreads

☐ Claim/update author profile on Goodreads

☐ Link all 7 books to your author profile

☐ Run a Goodreads Giveaway (1-5 free copies for reviews)

## 5.4 Newsletter Swaps

☐ Find 5 Christian fiction authors with email lists (search KDP categories)

☐ Propose cross-promotion: you feature them, they feature you

☐ Prepare swap copy (your book description + buy link)

# Phase 6: Church Network Activation (Your Unfair Advantage)

No other self-published author has this. The church donation model is unique.

☐ Sunday: Pitch ACAT to your pastor — explain the 50% donation model

☐ Sunday: Get on church bulletin/announcements

☐ Week 1: Start an ACAT small group reading study (Santa coordinates)

☐ Week 2: Order 10 ACAT paperback copies ($70 — done ✅) for church members

☐ Week 3: Church members leave Amazon reviews after reading

☐ Week 4: Expand to 3 more churches in Brevard County

☐ Month 2: Guest speaker at church events — talk about faith + fiction

☐ Month 3: Partner with Christian bookstores (Family Christian, Lifeway)

☐ Ongoing: Every church reader = potential email subscriber + reviewer + word-of-mouth marketer

The church network is your unfair advantage because: (1) it's genuine word-of-mouth, (2) it's free, (3) it builds credibility that money can't buy, (4) it produces reviews from real readers, and (5) it aligns with your mission — 50% of proceeds go to church outreach.

# Year 1 Target

## Revenue Targets

Conservative projections from the strategy doc:

| Metric | Target |
| --- | --- |
| Year 1 Revenue | $2,400 - $6,000 |
| Email Subscribers | 500+ |
| Amazon Reviews (ACAT) | 30+ |
| Amazon Reviews (all books) | 50+ |
| Monthly Ad Spend | $450/month max |
| Net Profit Margin | 60-70% (no inventory costs) |
| Church Partners Activated | 3-5 churches |

## Metrics Dashboard (Ben Affleck tracks these)

☐ Monthly sales revenue per book

☐ KU page reads (shows reader engagement)

☐ Email subscriber growth

☐ New reviews and average rating

☐ Ad spend and ACoS (ACoS = ad spend ÷ revenue)

☐ Church partners recruited

☐ Net profit after costs (books, ads, mileage)

# Reference Documents

All files available at https://192.168.1.126:8443/

| Document | Description |
| --- | --- |
| amazon_kdp_strategy.docx | Full 7-phase battle plan (read this first) |
| acat_launch_day_plan.docx | Hour-by-hour ACAT launch timeline |
| catch22_ads_guide.docx | Amazon Ads campaign setup + keyword lists |
| catch22_drafts.docx | Query letter drafts for traditional publishers |
| ACAT_First_3_Chapters.docx | Sample chapters for submissions |
| ACAT_Manuscript.rtf | Full ACAT manuscript (681KB) |
| ACAT_Author_Bio.docx | Updated author biography |
| baen_submission_package.docx | Baen Books traditional publisher submission |

# The Big Picture: 3-Pronged Publishing Strategy

You have three paths running in parallel. This document covers Prong 3 only. The other two paths run independently:

Prong 1: Literary Agent

Querying agents with personalized letters. Reference: catch22_drafts.docx has draft query letters. This runs in the background while you self-publish.

Prong 2: Traditional Publisher

Direct submissions to publishers (e.g., Baen Books). Reference: baen_submission_package.docx. A traditional deal would mean an advance + wider distribution.

Prong 3: Amazon KDP Self-Publishing ← ACTIVE FOCUS

Full control, 60-70% royalties, no gatekeepers, no waiting. You can build momentum now and let the other two paths catch up. If a traditional offer comes, you evaluate it from a position of strength — you already have sales data, reviews, and an audience.

The path is clear. Start with Phase 0. Work through each checkbox. Mark them off as you go.